## Action Log Tasks
ID | Order | Task | Final Category | Sub Category | Deadline slot | Condition | Owner | Contact | Suggestion | Action label | Action URL | Notes | Status | Comments
1 | 1 | Review and discuss the offer with Host line manager and Host PBP | Offer | Offer | Predefined | untilpredefineddate | Expat | GM |  |  |  | Expat has a "Document cabinet" in the Portal and inside they can find their PDF Offer | Active | Predefined are date manually added by the mobility by expat according to each process. Data format, check expat profile with final date
2 | 2 | Confirm offer acceptance | Offer | Offer | Predefined | untilpredefineddate | Expat | GM |  |  |  | Expat has button that confirms offer acceptance - this flows into an e-mail to GM/PBP | Active | Predefined are date manually added by the mobility by expat according to each process. Data format, check expat profile with final date
3 | 3 | Have an Onboarding call with Global Mobility | Offer | Onboarding | Predefined | untilpredefineddate | Expat | GM |  |  |  | Expat is tagged to their GM specialist and the system can show 5 available slots in the Outlook of the GM team, and Expat can click directly on the Portal and Outlook gets booked | Active | Predefined are date manually added by the mobility by expat according to each process. Data format, check expat profile with final date
4 | 4 | Review and sign the Letter of Assignment through DocuSign | Offer | Letter of Assignment | Predefined | untilpredefineddate | Expat | GM | Link to DocuSign |  |  | Ok | Active | Predefined are date manually added by the mobility by expat according to each process. Data format, check expat profile with final date
5 | 5 | Have an Immigration briefing with Vialto | Immigration | Immigration | 90-120d |  | Expat | Vialto | Link to myMobilityHQ for scheduling the call with Vialto immigration team | Schedule on myMobilityHQ | https://mymobility.vialto.com/ | Ok + contact details of Immigration team provided by Vialto | Active
6 | 6 | Gather and share personal Immigration documents required | Immigration | Immigration | 90-120d |  | Expat | Vialto | Link to myMobilityHQ for the document checklist | Document checklist | https://mymobility.vialto.com/ | Ok | Active
7 | 7 | Schedule the Tax & Equity briefing with Home & Host Vialto Tax team | Immigration | Tax | 90-120d | hasTaxConcerns | Expat | Vialto | Link to myMobilityHQ for scheduling the call with Vialto tax team | Schedule tax briefing | https://mymobility.vialto.com/ | Ok + contact details of Tax team provided by Vialto | Active
8 | 8 | Have a briefing with K2 about your and family's needs in the Host location | Relocation preparation | Destination Services | 90-120d |  | Expat | K2 | K2 contact email attached or a link to Apro with drafted template for scheduling this call, the template should have the K2 contact person implemented automatically |  |  | Check with K2 what we can implement - automated Outlook connect, or something else? | Active
9 | 9 | Plan the Look & See trip and align logistics with K2 | Relocation preparation | Destination Services | 90-120d |  | Expat | K2 | K2 contact email attached or a link to Apro for the checklist, eg. Visa, hotel booking, calendar for the 3 or 5 days with K2, etc. |  |  | K2 to provide PDF document with Look & See agenda/provide K2 contact details | Active
10 | 10 | Review the final visa application package and confirm/submit the application | Immigration | Immigration | 90-120d | hasImmigration | Expat | Vialto | Insert a due date for the visa submission in order to meet the target assignment start date. | Open myMobilityHQ | https://mymobility.vialto.com/ | Ok + link to Vialto My Mobility | Active
11 | 11 | Connect with Net Expat for Intercultural Training and Partner Support | Relocation preparation | Destination Services | 60d | needsIntercultural | Expat | Net Expat | Add the contact email for NetExpat consultant | Net Expat website | https://www.netexpat.com/ | Ok + website of Net Expat | Active
12 | 12 | Attend the Look & See trip | Relocation preparation | Destination Services | 60d |  | Expat | K2 | These two tasks can be combined as normally the preferred living area can be confirmed during or right after look & see trip. |  |  | Ok | Active
13 | 13 | Confirm the preferred living area at host with K2 | Relocation preparation | Destination Services | 60d |  | Expat | K2 |  |  |  | Ok | Active
14 | 14 | Schedule pre-move survey for HHG shipment | Relocation preparation | Destination Services | 60d |  | Expat | K2 | Add the contact email for moving company. Best to create a shipment status tracking sheet or checklist through Apro link which K2 can update the shipment status on real time. |  |  | K2 to provide live self-service visibility of the shipping process status | Active
15 | 15 | Submit school application | Relocation preparation | Destination Services | 60d | hasChildren | Expat | K2 |  |  |  |  | Active
16 | 16 | Organise Pet Shipment | Relocation preparation | Destination Services | 60d | hasPets | Expat | K2 | Add K2 contact |  |  | Some guidance would be helpful, and K2 contact to support | Active
17 | 17 | Conduct final health check and identify any medical needs in the Host | Relocation preparation | Healthcare | 60d |  | Expat | Expat |  |  |  | Ok - personal, not connected to ABI | Active
18 | 18 | Identify memberships/leases/etc that need to be reviewed/cancelled in Home country | Relocation preparation | Departure | 60d |  | Expat | Expat |  |  |  | We can provide some examples for inspiration e.g. gym membership, etc | Active
19 | 19 | Conduct the Packing of Household Goods with K2 | Relocation preparation | Departure | 60d |  | Expat | K2 | Link to the shipment status tracking sheet/checklist for real-time status update |  |  | OK | Active
20 | 20 | Organise Temporary Living in Home/Host with K2 | Relocation preparation | Destination Services | 60d | needsTempHousing | Expat | K2 |  |  |  | Check with K2: how can they provide visibility into the Temp Living options except by e-mail? | Active
21 | 21 | Provide documents required for customs clearance | Relocation preparation | Destination Services | 60d |  | Expat | K2 | Link to the shipment status tracking sheet/checklist for real-time status update |  |  | OK | Active
22 | 22 | Receive Immigration confirmation and align with Vialto on post-arrival immigration | Immigration | Immigration | 30d | hasImmigration | Expat | Vialto | Link to myMobilityHQ for downloading the visa | Download visa | https://mymobility.vialto.com/ | OK | Active
23 | 23 | Book final move ticket after visa is issued | Relocation preparation | Travel | 30d |  | Expat | GM | Insert a due date based on the target assignment start date |  |  | URL for Egencia | Active
24 | 24 | Relocate to the Host location with your family | arrivel | Travel | 30d |  | Expat | gm |  |  |  |  | Active
25 | 25 | Move into Temporary Housing | arrivel | Destination Services | arrival | needsTempHousing | Expat | k2 | Add a reminder for total temp living days entitled. |  |  | Ok | Active
26 | 26 | Open bank account in Host country | arrivel | Destination Services | arrival |  | Expat | K2 | Add a reminder for assignee to update the bank account information in WD |  |  | Ok | Active
27 | 27 | Follow guidance from Vialto for any post-arrival immigration process | Settle-in | Immigration | arrival | hasImmigration | Expat | Vialto | Link to Vialto email for post-arrival process. Suggest Vialto to upload all milestone emails to myMobilityHQ so Concierge can create the link to myMobilityHQ. | Post-arrival guidance | https://mymobility.vialto.com/ | Ok | Active
28 | 28 | Follow guidance from K2 for any post-arrival processes | Settle-in | Destination Services | arrival |  | Expat | K2 |  |  |  |  | Active
29 | 29 | Move into Permanent Housing | Settle-in | Destination Services | arrival |  | Expat | K2 | Suggest to implement a function for triggering an email reminder to Mobility Specialist once assignees clicks Complete on this task because in some countries, reporting address change is a legal/immigration requirement (for example, foreigners in China needs to report address change within 10 days to the immigration authority). |  |  | Ok | Active
30 | 30 | Arrange Household Goods delivery | Settle-in | Destination Services | arrival |  | Expat | K2 | Link to the shipment status tracking sheet/checklist for real-time status update |  |  | Ok | Active
31 | 31 | Schedule Language Training | Settle-in | Destination Services | arrival | hasLanguageBarrier | Expat | K2 | Add K2 contact |  |  | Ok | Active
32 | 32 | Register Cigna Envoy after receiving Cigna Welcome Email | Settle-in | Healthcare | arrival |  | Expat | Cigna | Add a reminder to the task. Normally Mobility Specialist should trigger Cigna enrollment after visa is granted so if assignee has not received Cigna Welcome Email after final arrival at Host, they should reach out to the Mobility team. |  |  | Link to Cigna Envoy | Active
33 | 33 | Review the drafted first host payroll with Global Mobility | Settle-in | Payroll | arrival |  | Expat | GM | Suggest to add a link to Mobility specialist's outlook calendar for scheduling this call |  |  | Book the slot with options connected to GM team's Outlook | Active
34 | 34 | Organise local Onboarding with line manager and local PBP | Settle-in | Onboarding | arrival |  | Expat | Host PBP |  |  |  | Show who is Host PBP and same option with Outlook invite slots | Active

## README
V4 Action Log Tasks — source of truth
Edit rows on the 'Action Log Tasks' sheet. The V4 demo reloads from this file on each request.
Condition flags (leave blank if always shown): hasTaxConcerns, hasImmigration, needsIntercultural, hasChildren, hasPets, needsTempHousing, hasLanguageBarrier
Set Status = Disabled to hide a task from the action log.
Deadline slot values: 90-120d, 60d, 30d, arrival